## START HERE
BIRDIES & ALIBIS - TOURNAMENT PLANNING WORKBOOK
Professional golf planning tools from Birdies & Alibis
https://birdiesandalibis.com
HOW TO USE THIS WORKBOOK
Use the green input cells. Replace fictional examples. Do not enter card or bank account numbers.
Workflow | Complete Event Setup; assign Timeline owners; build Budget; track Sponsors and Registration; finalize Teams, Volunteers, Contests, Check-In and Run Sheet; close with Reconciliation.

## EVENT SETUP
TOURNAMENT EVENT SETUP
Decision | Your answer | Owner | Deadline
Purpose / fundraising goal
Tournament name
Date and course
Format
Capacity and player fee
Tee times or shotgun
Registration deadline
Refund / substitution policy

## TIMELINE
16-WEEK TOURNAMENT TIMELINE
Target | Task | Owner | Due date | Status
16-12 weeks | Reserve course; approve purpose, goal, format and budget |  |  | Not started
12-10 weeks | Set sponsor packages, prices, terms and promotion |  |  | Not started
10-8 weeks | Open registration and sponsor outreach |  |  | Not started
8-4 weeks | Order signs, signs and prizes; recruit volunteers |  |  | Not started
4-2 weeks | Confirm players, payments, teams and vendors |  |  | Not started
Final week | Freeze print files and assign check-in roles |  |  | Not started
Within 7 days after | Reconcile funds and thank sponsors and golfers |  |  | Not started

## BUDGET
TOURNAMENT BUDGET
Category | Item | Quantity | Unit amount | Projected | Actual
Revenue | Player/team entries | 36 | 400 | 0
Revenue | Sponsors | 8 | 500 | 0
Revenue | Mulligans/add-ons | 100 | 20 | 0
Expense | Golf, carts and food | 144 | 85 | 0
Expense | Prizes, signs and supplies | 1 | 2500 | 0
SUMMARY | Projected revenue |  |  | 0
SUMMARY | Projected expenses |  |  | 0
SUMMARY | Projected net proceeds |  |  | 0

## SPONSORS
SPONSOR FULFILLMENT
Sponsor ID | Sponsor | Level | Amount | Paid? | Logo received? | Benefits promised | Delivered? | Owner
S001 | Example Sponsor | Hole | 500 | Yes | Yes | Hole sign | No | Jordan
S002 |  |  |  | No | No |  | No

## REGISTRATION
PLAYER REGISTRATION
Registration ID | Player name | Email | Phone | Team ID | Handicap | Paid? | Amount | Special request | Checked in?
R001 | Jordan Fairway | jordan@example.com | 555-0100 | T001 | 8.2 | Yes | 125 |  | No
R002 | Casey Links | casey@example.com | 555-0101 | T001 | 12.4 | Yes | 125 |  | No

## TEAMS
TEAMS AND STARTING ASSIGNMENTS
Team ID | Team name | Player 1 | Player 2 | Player 3 | Player 4 | Start type | Tee time / hole
T001 | Fairway Friends | R001 | R002 |  |  | Shotgun | 1A
T002 | [5 empty] | Shotgun | 1B

## VOLUNTEERS
VOLUNTEER ASSIGNMENTS
Volunteer | Mobile | Assignment | Report time | Location | Lead | Confirmed? | Notes
Alex Green | 555-0102 | Registration | 7:00 AM | Clubhouse | Jordan | Yes
No

## CONTESTS
CONTESTS, PRIZES AND EXTRAS
Type | Name / hole | Eligibility | Places | Prize / payout | Winner | Verified by | Notes
Closest to pin | Hole 4 | All players | 1 | Gift card
Low gross | Overall | All players | 3 | Trophies
Extra | Mulligan package | Per player |  | $20

## CHECK-IN
TOURNAMENT CHECK-IN
Registration ID | Player | Team | Arrived? | Entry paid? | Mulligans | Other extras | Amount due | Notes
R001 | Jordan Fairway | T001 | No | Yes | 0 |  | 0
R002 | Casey Links | T001 | No | Yes | 0 |  | 0

## RUN SHEET
TOURNAMENT-DAY RUN SHEET
Time | Action | Owner | Backup | Location | Complete? | Issue / resolution
7:00 AM | Open check-in and payment stations |  |  | Clubhouse | No
8:15 AM | Player briefing and announcements |  |  | Practice green | No
8:30 AM | Shotgun start |  |  | Course | No
1:30 PM | Score deadline and awards preparation |  |  | Clubhouse | No

## RECONCILIATION
POST-EVENT RECONCILIATION
Area | Expected | Actual | Difference | Owner | Resolved? | Notes
Registration revenue | 18000 | 18000 | 0 |  | Yes
Sponsor revenue | 4000 | 4000 | 0 |  | Yes
Extras | 2000 | 1900 | 0 |  | No
Course and event expenses | 14740 | 14740 | 0 |  | Yes
NET PROCEEDS | 0 | 0 | 0